## detail
Detail Estimation for Construction of Store
Sl. No | Code | Item Description | Nos | L | B | H | Quantity | Unit | Rate | Amount
1 | CG0002 | Uprooting of vegetation & trees of girth < 300mm & disposal within 50m of the site | 1 | 8 | 5 |  | 40 | Sq.m | 9.1 | 364
2 | EW0031 | Earth work in excavation over areas, depth >300mm, width >1.5m, area >10 Sq.m on plan, including disposal of excavated earth within 50m lead and 1.5m lift & disposed soil to be neatly dressed -Hard Soil. | 2 | 5.5 | 0.6 | 0.55 | 3.63 | Cum
|  |  | 2 | 2.45 | 0.6 | 0.55 | 1.617
[7 empty] | 5.247 | cum | 151.16 | 793.1365
3 | EW0195 | Filling of trenches, sides of foundations etc. in layers<200mm using selected excavated earth, including compaction by ramming etc. within lead 50 m & lift 1.5m | 2 | 7.95 | 0.275 | 0.55 | 2.4049
|  |  | 1 | 5 | 3 | 0.3 | 4.5
[7 empty] | 6.9049 | cum | 80.29 | 554.3924
4 | SM0072 | Providing and laying Hand packed stone filling or soling with stones | 2 | 5.5 | 0.6 | 0.15 | 0.99
|  |  | 2 | 2.45 | 0.6 | 0.15 | 0.441
[7 empty] | 1.431 | cum | 1341 | 1918.971
5 | SM0005 | Providing & laying Random Rubble Masonry with hard stone in foundation & plinth -In cement mortar 1:5 | 2 | 5.5 | 0.4 | 0.6 | 2.64
|  |  | 2 | 2.5 | 0.4 | 0.6 | 1.2
[7 empty] | 3.84 | Cum | 3199.4 | 12285.696
6 | CW0006 | Providing and laying in position plain cement concrete 1:3:6 (1 cement : 3 sand : 6 graded crushed stone 20 mm nominal size) excluding the cost of centering and shuttering - All work upto plinth level under footings-100mm thick. | 1 | 5 | 3 | 0.1 | 1.5 | Cum | 4090.64 | 6135.96
7 | CW0006 | Providing and laying in position plain cement concrete 1:4:8 excluding the cost of centering and shuttering - All work upto plinth level under footings-100mm thick. | 2 | 5.5 | 0.6 | 0.1 | 0.66
|  |  | 2 | 2.45 | 0.6 | 0.1 | 0.294
[7 empty] | 0.954 | cum | 3471.03 | 3311.3626
Sl. No | Code | Item Description | Nos | L | B | H | Quantity | Unit | Rate | Amount
8 | RC0083 | Providing & fixing Thermo-Mechanically Treated reinforcement bar (Yield Strength 500 MPa) for R.C.C work including cutting, bending, binding and placing in position complete
|  | Column- 16mm dia - 4 Nos | 4 | 3.1 | wt/m | 1.578 | 19.5672 | kg | 66.01 | 1291.6309
9 | RF0003 | Fixing Corrugated Galvanised Iron (CGI) sheeting, including bolts, hooks and nuts 8mm dia. with bitumen and G.I limpet washers filled with white lead for connection, excluding the cost of purlins, rafter and trusses (CGI sheets will be provided by BT) | 1 | 5 | 3 |  | 15 | Sqm | 93.75 | 1406.25 | 0
10 | WW0060 | Providing & fixing roof framing, in trusses, purlins, rafters, posts, post plates including hoisting, etc. (excluding steel items)- Mixed Conifer
|  | rafter | 5 | 3.4 | 0.1 | 0.1 | 0.17
|  | purlins | 4 | 5.6 | 0.075 | 0.05 | 0.084
[7 empty] | 0.254 | cum | 21517 | 5465.318
11 | BW0021 | Providing & laying Second-Class Half-brick Masonry (125 mm) in superstructure below floor 2 level | 2 | 5 |  | 2.35 | 23.5
|  |  | 2 | 3 |  | 2.35 | 14.1
37.6
|  | Deduction for window | 1 | 2 |  | 1.2 | 2.4
[7 empty] | 35.2 | sqm | 728.24 | 25634.048
12 |  | Providing & laying Second-Class Brick work in Foundation & Plinth in CM 1:5- steps | 2 | 1.6 | 0.25 | 0.15 | 0.12
|  | corner columns | 4 | 0.25 | 0.25 | 2.35 | 0.5875
[7 empty] | 0.7075 | cum | 5188 | 3670.51
13 | PL0041 | Providing & laying 20mm cement plaster on rough side of single or half-brick wall C.M 1:5 | 1 | 18 |  | 2.35 | 42.3
|  | deductions - door | 1 | 1.2 |  | 2.1 | 2.52
|  | window | 1 | 2 |  | 1.2 | 2.4
37.38
|  | both inside and outside |  |  |  |  | 74.76 | sqm | 93.88 | 7018.4688
14 |  | Providing & fixing in position dressed wood work in frames of doors, windows, clerestory windows and other frames, wrought and framed. Mixed conifer- 25mm | 1 | 1.2 |  | 2.1 | 2.52
|  |  | 1 | 2 |  | 1.2 | 2.4
[7 empty] | 4.92 | sqm | 1231 | 6056.52
Sl. No | Code | Item Description | Nos | L | B | H | Quantity | Unit | Rate | Amount
Maintenance of existing room
15 |  | Providing & laying Second-Class Half-brick Masonry (125 mm) in superstructure
|  |  | 1 | 3.35 |  | 3.15 | 10.5525
|  | deduction for door | 1 | 1.2 |  | 2.1 | 2.52
|  | Net qty |  |  |  |  | 8.0325 | sqm | 728.24 | 5849.5878
16 |  | Providing & fixing in position dressed wood work in frames of doors, windows, clerestory windows and other frames, wrought and framed -Mixed conifer- 25mm | 1 | 1.2 |  | 2.1 | 2.52 | sqm | 1231 | 3102.12
17 |  | Providing & laying 20mm cement plaster on rough side of single or half-brick wall C.M 1:5 |  |  |  |  | 16.065 | sqm | 93.88 | 1508.1822
|  | Total Amount | [7 empty] | 86366.1542
Note on J4: Author: bsr rate